## Gantt chart
		2021
	Project Timeline (months)	Feb-21	Mar-21	Apr-21	May-21	Jun-21	Jul-21
WP	Description	1	2	3	4	5	6
Commencment of Project
1	Idea formulation
	Task 1.1 Discussion with lecturer
	Task 1.2 Find literature sources
	Task 1.3 Initial reading about main topic
2	Literature Review
	Task 2.1 Identify and review relevant technologies
	Task 2.2 Review other studies/projects
	Task 2.3 Compare and contrast
3	Methodology
	Task 3.1 Hypothesis and Research Questions
	Task 3.2 Research Pipeline
	Task 3.3 Storyboard, assets identification, design requirements and approach
	Task 3.4 Specifications
4	Application development
	Task 4.1 Build Dataset
	Task 4.2 Train AI model
	Task 4.3 Test and evaluate model
	Task 4.4 Refine model
5	Deliverables
	Task 5.1 IEEE paper

Project Closure

	Notes