## Projected
		15th Feb	22nd Feb	1st Mar	8th Mar	15th Mar	22nd Mar	29th Mar	12th Apr	19th Apr	26th Apr	3rd May	10th May	17th May	24th May	31st May

WP	Task	Wk1	Wk2	Wk3	WK4	WK5	WK6	Easter	WK7	WK8	WK9	WK10	WK11	WK12	WK13	WK14
Report
	Create an account
	Load template
	Read guidelines

Deliverables
	Create GIT Account
	Share with lecturer
	Commit regularly
	Record prototype
	Upload VIVA
	Submit report

Research Methodology
	Hypothesis
	Research Questions
	Research Methods
	Research Pipeline
	Finalise section in report

Literature Review
	Review datasets
	Review algorithms
	Review evaluation metrics
	Finalise section in report

Prototype
	Find tutorial
	Replicate tutorial
	Create custom dataset
	Tweek prototype
	Generate evaluation results

Discussion of Results
	Write prototype evaluation
	Write dataset evaluation
	Write hypothesis testing
	Write project evaluation
	Finalise section in report

Other sections (Conclusion, Introduction, Abstract)
	Finalise conclusion & recommendations
	Finalise Introduction
	Finalise Abstract

## Actual
Darryl Bonnici		15th Feb	22nd Feb	1st Mar	8th Mar	15th Mar	22nd Mar	29th Mar	12th Apr	19th Apr	26th Apr	3rd May	10th May	17th May	24th May	31st May

WP	Task	Wk1	Wk2	Wk3	WK4	WK5	WK6	Easter	WK7	WK8	WK9	WK10	WK11	WK12	WK13	WK14
Report
	Create an account																No issues
	Load template																No issues
	Read guidelines																No issues

Deliverables
	Create GIT Account																No issues
	Share with lecturer																Shared the idea at first, then in week 11 had a seperate meeting to show progress on prototype.
	Commit regularly																Commits couldnt be done regularly due to apprenticeship and other commitments. But Tutorial process was going on.
	Record prototype																This was done after all changes have been made and everything was finalized.
	Upload VIVA																This was done after all changes have been made and everything was finalized.
	Submit report

Research Methodology
	Hypothesis																This was evaluated later on as ideas changed after the course of the tutrial process.
	Research Questions																Many options to chose from however needed some time to decide what to focus on.
	Research Methods
	Research Pipeline
	Finalise section in report

Literature Review
	Review datasets																Data sets where looked at – however due to the viva process, I had to find something to show in real time therefore this had to be changed and create custom datasets
	Review algorithms																This was done during the tutorial phase
	Review evaluation metrics																This was done during the tutorial phase
	Finalise section in report																Finding Literature that was related to the subject matter and reading through them took some time.

Prototype
	Find tutorial																Tutorials where easy to find but difficult to follow as most videos are hours long.
	Replicate tutorial																Took some time to find a good tutorial that explained what was happening and as the tutorial was hours long and slight out-dated, errors were encountered during the replication of the tutorial.
	Create custom dataset																Custom Data set took some time due to the labeling and testing performance on images taken by myself , which then had to download selected custom data sets.
	Tweek prototype																Prototype needed little to no tweaking
	Generate evaluation results

Discussion of Results
	Write prototype evaluation																This was left to last as during the prototype things could have changed whilst also considering that writing is not my strong suite. Prototype tweaking was more important at this stage
	Write dataset evaluation																This was left to last as during the prototype things could have changed whilst also considering that writing is not my strong suite. Prototype tweaking was more important at this stage
	Write hypothesis testing																This was left to last as during the prototype things could have changed whilst also considering that writing is not my strong suite. Prototype tweaking was more important at this stage
	Write project evaluation																This was delayed due to other assignments.
	Finalise section in report																This was delayed due to other assignments.

Other sections (Conclusion, Introduction, Abstract)																	This was delayed due to other assignments.
	Finalise conclusion & recommendations																This was delayed due to other assignments.
	Finalise Introduction																This was delayed due to other assignments.
	Finalise Abstract																This was delayed due to other assignments.